## Sheet1
Release 1 Schedual
Activity | Duration | Start Date | End Date | Team Member
Documentation
Create the draft document | 1 Hour | Monday,06/08/2018 | Monday,06/08/2018 | All
Write the document | 3 Weeks | Monday,13/08/2018 | Friday,31/08/2018 | All
individual logs book writing | 2 Days | Wednesday,29/08/2018 | Friday,31/08/2018 | All
Review and revise project document | 2 Days | Saturday, 01/09/2018 | Sunday,02/09/2018 | All
Design
Create use story and map | 2 Days | Monday,13/08/2018 | Tusday,14/08/2018 | All
Create Use Cases Narratives | 2 Days | Wednesday,15/08/2018 | Thursday,16/08/2018 | All
Create Agile Requirements and non- functional requirement | 2 Days | Friday,17/08/2018 | Sunday,19/08/2018 | All
Create System Architecture diagram | 2 Days | Monday,20/08/2018 | Wednesday,22/08/2018 | All
Create data relate diagram and dictionary | 2 Days | Thursday,23/08/2018 | Saturday,25/08/2018 | All
Calculate the cost | 2 Days | Sunday,26/08/2018 | Tusday,28/08/2018 | All
Implementation
Create the basic structure and function of the system | 3 Weeks | Monday,13/08/2018 | Friday,31/08/2018 | All
Testing
Test the system | 2 Days | Saturday, 01/09/2018 | Sunday,02/09/2018 | All
Deployment
Present the document and the system to the tutor | 1 Hour | Wednesday,05/09/2018 | Wednesday,05/09/2018 | All